## GOODS PROCUREMENT PLAN
Procurement Entity : West African Genetic Medicine Centre, University of Ghana
Budget Period: JANUARY,2021-DECEMBER,2021
Source of Funding : World Bank Africa Centres of Excellence Project
|  |  |  | Qty | BASIC DATA |  |  | TENDERING PERIOD |  |  | TENDER EVALUATION & CONTRACT AWARD
No. | Contract Package | Plan vs | Package No. |  | Estimated | Procurement | Approval/ | Preparation | Tender | Tender | Sub. Ten. | Approval by | Contract | Delivery | Inspection
|  | Actual |  |  | Amount(USD) | Method | Authority | Ten. Doc | Invitation Date | Closing/Open. | Eva. Report. | Authority | Date | Date | Final Accept.
|  | Duration | [5 empty] | 0 - 4 WKS | 1 - 2 WKS | 6 - 12 WKS | 1.5 -3 WKS | 1 - 1.5WKS | 1WKS | 1 - 3 WKS
1 | NextSeq 550 Illumina Sequencer system | Plan | UG/WAGMC/ACE/SS/001/21 | 1 | 300000 | SS | HOE | 2021-01-04 | 2021-01-18 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-23 | 2021-03-30
Actual
2 | Office Equipment, Stationery,Printing and General Supplies (PQ:Procure in Batches as when needed) | Plan | UG/WAGMC/ACE/PQ/002/21 | Vrs | 50000 | PQ | HOE | 2021-02-05 | 2021-02-12 | 2021-03-05 | 2021-03-12 | 2021-03-19 | 2021-03-26 | 2021-04-09 | 2021-04-16
Actual
3 | Microscopes and Laboratory Equipment (PQ:Procure in Batches as when needed) | Plan | UG/WAGMC/ACE/PQ/003/21 | Vrs | 50000 | PQ | HOE | 2021-03-15 | 2021-03-22 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-17 | 2021-05-24
Actual
4 | ICT Equipment ,Softwares & Accessories | Plan | UG/WAGMC/ACE/NCT/004/21 | Vrs | 60000 | NCT | HOE | 2021-01-12 | 2021-01-19 | 2021-02-09 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-16 | 2021-03-23
Actual
5 | General Laboratory Reagents and Consumables (PQ:Procure in Batches as when needed) | Plan | UG/WAGMC/ACE/PQ/005/21 | Vrs | 120000 | PQ | HOE | 2021-04-08 | 2021-04-15 | 2021-05-06 | 2021-05-17 | 2021-05-27 | 2021-06-03 | 2021-06-17 | 2021-06-24
Actual
6 | Office Furniture (PQ:Procure in Batches as when needed) | Plan | UG/WAGMC/ACE/PQ/006/21 | Vrs | 25000 | PQ | HOE | 2021-02-09 | 2021-02-16 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06
Actual
7 | Telehealth Platform(Hardware and Software System) | Plan | UG/WAGMC/ACE/NCT/007/21 | Vrs | 40000 | NCT | ETC | 2021-05-03 | 2021-05-10 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05
Actual
8 | Ultrasound System-Vivid IQ | Plan | UG/WAGMC/ACE/SS/008/21 | 1 | 40000 | SS | HOE | 2021-06-18 | 2021-06-25 | 2021-07-16 | 2021-07-23 | 2021-07-30 | 2021-08-06 | 2021-08-13 | 2021-08-20
Actual
| TOTAL |  |  |  | 685000
| ETC | Entity Tender Committee
| NCT | National Compettitive Tender
| PQ | Price quotation
| SS | Sole Sourcing
| HOE | Head of Entity

## WORKS PROCUREMENT PLAN
Procurement Entity : West African Genetic Medicne Centre, University of Ghana
Budget Period: Jan 2021 - December 2021
Source of Funding : World Bank Africa Centres of Excellence Project
|  |  |  | BASIC DATA |  |  | TENDERING PERIOD |  |  | TENDER EVALUATION & CONTRACT AWARD
No. | Contract Package | Plan vs | Package No. | Estimated (USD) | Procurement Method | Approval/Authority | Preparation | Tender | Tender | Sub. Ten. | Approval by | Contract | Delivery | Inspection
|  | Actual |  |  |  |  | Ten. Doc | Invitation Date | Closing/Open. | Eva. Report. | Authority | Date | Date | Final Accept.
|  | Duration |  |  |  |  | 0 - 4 WKS | 1 - 2 WKS | 6 - 12 WKS | 1.5 -3 WKS | 1 - 1.5WKS | 1WKS | 1 - 3 WKS
1 | Refurbishment of Laboratories &Lecture Rooms | Plan | UG/WAGMC/ACE/WKS/PQ//001/21 | 50000 | PQ | HOE | 2021-03-04 | 2021-03-18 | 2021-04-08 | 2021-04-15 | 2021-04-22 | 2021-04-29 | 2021-05-27 | 2021-06-03
Actual
2 | Construction of Vivarium | Plan | UG/WAGMC/ACE/WKS/NCT/002/21 | 60000 | NCT | ETC | 2021-02-17 | 2021-03-03 | 2021-03-24 | 2021-04-07 | 2021-04-14 | 2021-04-21 | 2021-05-19 | 2021-05-26
Actual
3 | Construction of WAGMC Building-Phase I | Plan | UG/WAGMC/ACE/WKS/NCT/003/21 | 330000 | NCT | ETC | 2021-04-26 | 2021-05-10 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-11-29 | 2021-12-06
Actual
3 | Construction of DNA Confirmation Unit | Plan | UG/WAGMC/ACE/WKS/PQ/004/21 | 30000 | PQ | ETC | 2021-06-15 | 2021-06-29 | 2021-07-20 | 2021-07-27 | 2021-08-03 | 2021-08-10 | 2021-08-17 | 2021-08-24
Actual
| TOTAL |  |  | 470000