## GOODS 2022
Procurement Entity : West African Genetic Medicine Centre, University of Ghana
Budget Period: JANUARY,2022-DECEMBER,2022
Source of Funding : World Bank Africa Centres of Excellence Project
|  |  |  | Qty | BASIC DATA |  |  | TENDERING PERIOD |  |  | TENDER EVALUATION & CONTRACT AWARD
No. | Contract Package | Plan vs | Package No. |  | Estimated | Procurement | Approval/ | Preparation | Tender | Tender | Sub. Ten. | Approval by | Contract | Delivery | Inspection
|  | Actual |  |  | Amount(USD) | Method | Authority | Ten. Doc | Invitation Date | Closing/Open. | Eva. Report. | Authority | Date | Date | Final Accept.
|  | Duration | [5 empty] | 0 - 4 WKS | 1 - 2 WKS | 6 - 12 WKS | 1.5 -3 WKS | 1 - 1.5WKS | 1WKS | 1 - 3 WKS
1 | Office Equipment, Stationery,Printing and General Supplies (PQ:Procure in Batches as when needed) | Plan | UG/WAGMC/ACE/PQ/001/22 | Vrs | 90000 | PQ | HOE | 2022-02-04 | 2022-02-11 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-15
Actual
2 | Laboratory Equipment (PQ:Procure in Batches as when needed) | Plan | UG/WAGMC/ACE/PQ/003/22 | Vrs | 50000 | PQ | HOE | 2022-03-15 | 2022-03-22 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-17 | 2022-05-24
Actual
3 | ICT Equipment & Accessories | Plan | UG/WAGMC/ACE/NCT/004/22 | Vrs | 60000 | NCT | HOE | 2022-01-12 | 2022-01-19 | 2022-02-09 | 2022-02-16 | 2022-02-23 | 2022-03-02 | 2022-03-16 | 2022-03-23
Actual
4 | General Laboratory Reagents and Consumables (PQ:Procure in Batches as when needed) | Plan | UG/WAGMC/ACE/PQ/005/22 | Vrs | 100000 | PQ | HOE | 2022-04-08 | 2022-04-15 | 2022-05-06 | 2022-05-17 | 2022-05-27 | 2022-06-03 | 2022-06-17 | 2022-06-24
Actual
5 | Office Furniture & Fittings (PQ:Procure in Batches as when needed) | Plan | UG/WAGMC/ACE/PQ/006/22 | Vrs | 25000 | PQ | HOE | 2022-02-09 | 2022-02-16 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-06
Actual
6 | Telehealth Platform(Hardware and Software System) | Plan | UG/WAGMC/ACE/NCT/007/22 | Vrs | 40000 | NCT | ETC | 2022-05-03 | 2022-05-10 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-06-22 | 2022-06-28 | 2022-07-05
Actual
| TOTAL |  |  |  | 365000
| ETC | Entity Tender Committee
| NCT | National Compettitive Tender
| PQ | Price quotation
| SS | Sole Sourcing
| HOE | Head of Entity
| CTRC | Central Tender Review Committee

## WORKS 2022
Procurement Entity : West African Genetic Medicne Centre, University of Ghana
Budget Period: Jan 2022 - December 2022
Source of Funding : World Bank Africa Centres of Excellence Project
|  |  |  | BASIC DATA |  |  | TENDERING PERIOD |  |  | TENDER EVALUATION & CONTRACT AWARD
No. | Contract Package | Plan vs | Package No. | Estimated (USD) | Procurement Method | Approval/Authority | Preparation | Tender | Tender | Sub. Ten. | Approval by | Contract | Delivery | Inspection
|  | Actual |  |  |  |  | Ten. Doc | Invitation Date | Closing/Open. | Eva. Report. | Authority | Date | Date | Final Accept.
|  | Duration |  |  |  |  | 0 - 4 WKS | 1 - 2 WKS | 6 - 12 WKS | 1.5 -3 WKS | 1 - 1.5WKS | 1WKS | 1 - 3 WKS
1 | Refurbishment of Laboratories &Lecture Rooms | Plan | UG/WAGMC/ACE/WKS/PQ/001/22 | 50000 | PQ | HOE | 2022-03-04 | 2022-03-18 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-27 | 2022-06-03
Actual
3 | Construction of WAGMC Building | Plan | UG/WAGMC/ACE/WKS/NCT/003/22 | 330000 | NCT | CTRC | 2022-01-05 | 2022-02-08 | 2022-04-12 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-07-14 | 2023-04-30
Actual
| TOTAL |  |  | 380000

## SERVICES 2022
Procurement Entity : West African Genetic Medicne Centre, University of Ghana
Budget Period: Jan 2022 - December 2022
Source of Funding : World Bank Africa Centres of Excellence Project
|  |  |  | BASIC DATA |  |  | TENDERING PERIOD |  |  | TENDER EVALUATION & CONTRACT AWARD
No. | Contract Package | Plan vs | Package No. | Estimated (USD) | Procurement Method | Approval/Authority | Preparation | Tender | Tender | Sub. Ten. | Approval by | Contract | Delivery | Inspection
|  | Actual |  |  |  |  | Ten. Doc | Invitation Date | Closing/Open. | Eva. Report. | Authority | Date | Date | Final Accept.
|  | Duration |  |  |  |  | 0 - 4 WKS | 1 - 2 WKS | 6 - 12 WKS | 1.5 -3 WKS | 1 - 1.5WKS | 1WKS | 1 - 3 WKS
1 | Consultancy Services ( Public Relation & Marketing Services for Genetic Health Awarness Campaign) | Plan | UG/WAGMC/ACE/SS/NCT/001/22 | 50000 | NCT | CTRC | 2022-01-04 | 2022-01-20 | 2022-08-05 | 2022-08-12 | 2022-08-26 | 2022-09-05 | 2022-09-12 | 2022-09-26
Actual
2 | Upgrade of WAGMC Website Services | Plan | UG/WAGMC/ACE/SS/PQ/002/22 | 10000 | PQ | HOE | 2022-07-04 | 2022-07-14 | 2022-08-05 | 2022-08-12 | 2022-08-26 | 2022-09-05 | 2022-09-12 | 2022-09-26
Actual
3 | Installation of Telehealth Software platforms | Plan | UG/WAGMC/ACE/SS/NCT/003/22 | 40000 | NCT | ETC | 2022-07-03 | 2022-07-14 | 2022-08-05 | 2022-08-13 | 2022-08-27 | 2022-09-05 | 2022-09-11 | 2022-09-26
Actual
4 | Procurement Audit Services | Plan | UG/WAGMC/ACE/SS/NCT/003/22 | 22000 | NCT | ETC | 2022-07-04 | 2022-07-14 | 2022-08-05 | 2022-08-12 | 2022-08-26 | 2022-09-05 | 2022-09-12 | 2022-09-26
Actual
5 | Financial Audit Services | Plan | UG/WAGMC/ACE/SS/NCT/004/22 | 22000 | NCT | ETC | 2022-07-04 | 2022-07-14 | 2022-08-05 | 2022-08-12 | 2022-08-26 | 2022-09-05 | 2022-09-12 | 2022-09-26
Actual
| TOTAL |  |  | 144000

## SUMMARY
WAGMC
PROCUREMENT PLAN FOR 2022
SUMMARY PROCUREMENT PLAN REPORT
PROCUREMENT PLAN
1 | GOODS | 365000
2 | SERVICES | 144000
3 | WORKS | 380000
4 | TOTAL | 889000