## Sheet1
Name of Center: West African Genetic Medicine Centre (WAGMC)
Institution: University of Ghana |  |  |  | On Schedule
Country: Ghana
Center Leader: Prof. Solomon Ofori-Acquah |  |  |  | Behind Schedule
Annual Workplan: 16-November-2020
Work Plan Activities | Description | Partner Contribution (if relevant) | 2021 Y2Q1 |  |  | 2021 Y2Q2 |  |  | 2021 Y2Q3 |  |  | 2021 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Establishing structures and facilities for good governance and administration\ DLI Action 1: Institutional Readiness
Sub-Action 1a: Refurbish and upgrade ICT infrastructure, website design, and hosting, purchase software, and upgrade WAGMC website
Activity 1: Refurbish and upgrade ICT infrastructure | Purchase equipment and software to improve ICT infrastructure through out the Centre | [13 empty] | 1. Improved access to internet service through out the Centre. 2.Develop Data base that make it easy to collect information on both students and faculty. 3. Digitize procurement process in the Centre to ensure timely procurement of supplies and consumable for staff, students and faculty. 4. Software for data management and analysis procured for researchers. |  | 30000 | 0 | 0 | Centre Leader, Project Manager, IT Officer, Procurement Officer, University of Ghana Computing Services (UGCS)
Activity 2: Upgrade WAGMC Website | Upgrade WAGMC website by constantly improving its design, functionality, interactivity and security features. | [13 empty] | 1. Improved information sharing with members of the Centre, partners and stakeholders. |  | 10000 | 0 | 0 | Centre Leader, Project Manager, IT Officer, Communications Officer
Activity 3: Purchase software and equipment | Purchase of computers, accessories and software that will improve the efficiency and productivity of the Administrative team as well as that of researchers of the Centre. | [13 empty] | 1. Appropriate equipment and software for staff to improve productivity and efficiency purchased. |  | 20000 | 0 | 0 | Centre Leader, Project Manager, IT Officer, Procurement Officer, UGCS
Sub-Action 1b: Set up International Scientific Advisory Board and expand the international faculty
Activity 1: Organize first meeting for International Scientific Advisory Board (ISAB) | ISAB will be meeting once a year to provide guidance and input on educational and research programs | ISAB Members to attend meeting. | [12 empty] | 1. Feedback from ISAB on progress of the Centre will help the Management of the Centre develop competitive programs and engage in relevant research activities. 2. Faculty and students will have the opportunity to participate in collaborative research in institutions the members of the ISAB are affiliated with. |  | 5000 | 0 | 0 | Centre Leader, Project Manager, IT Officer, Communications Officer
Sub-Action 1c: Support Administrative Staff of the Centre to upgrade their professional qualifications
Activity 1: Support staff to participate in career development and educational programs | Staff at the Centre will be supported to participate in various educational programs, workshops, seminars and conferences that will help improve their efficiency and productivity at the Centre. | [13 empty] | 1. Improved efficiency and productivity of staff members in the Centre. 2. Growth of potential and career advancement. | Administrative staff are essential to the efficient and successful running of the Centre. It is crucial that they are equipped with the skills and knowledge they require to play their roles to the best of their abilities. Staff at the Centre should also be supported to improve themselves professionally ensuring career advancement, ability and opportunity to grow into senior roles and become more marketable. | 70000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager
Sub-Action 1d: Efficient management of Centre Administration and activities
Activity 1: Maintaining daily operations of the Centre by organising, planning and executing Centre activities, procuring office supplies, equipment, fuel and other goods and services and employing additional personnel | The Centre managemement has determined that it needs to employ specific people within the Centre to work with University staff to advance two major acivities. A Facilities Manager is needed to accelerate all aspects of the building project, and to also oversee the installation and maintenance of all faclities and equipment of the Centre. A Biomedical Procurement Specialist is needed to work with Fellows, and Centre researchers to optimize procurement of supplies to advance the work of the Centre. Qualified individuals will be hired in the current year through a competitive process. | [13 empty] | 1. First Phase of the WAGMC Building complex begins 2. Improved management of procurement activities of the Centre, timely completion of projects and graduation of students | WAGMC is committed to ensuring it meets the milestones outlined in the DLIs. Two major activities (the WAGMC Building Complex and Procurement related activities) over the past year and half have been negatively impacted and crossly delayed due to the overstretched support system at the University. It has become apparent that the Centre will have to employ two key personnel to move these activities along. | 150000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, ESS Officer, Procurement Officer, HR unit of the College of Health Sciences
Action 2: Improving the infrastructure and environment for teaching, learning and research\DLI Action 4: Quality of Education and Research
Sub-Action 2a: Upgrade Seminar and Lecture Rooms
Activity 1: Refurbish seminar and lecture rooms | Selected seminar and lecture rooms of anchor and affiliate departments will be refurbished to make them more conducive and comfortable for use by students and faculty. | [13 empty] | 1. Refurbished lecture and seminar rooms |  | 25000 | 0 | 0 | Centre Leader, Project Manager, Procurement Officer, M&E Officer
Activity 2: Procure equipment and furniture | Equipment and software that will improve delivery and active participation of students in lectures and seminars. | [13 empty] | 1. Lecture and seminar equipment purchased |  | 25000 | 0 | 0 | Centre Leader, Project Manager, Procurement Officer, M&E Officer
Sub-Action 2b: Upgrade Laboratories
Activity 1: Refurbish laboratories | Laboratories will be refurbished to make them more conducive and comfortable for use by students and faculty. | [13 empty] | 1. Refurbished Laboratories |  | 25000 | 0 | 0 | Centre Leader, Project Manager, Procurement Officer, M&E Officer
Activity 2: Procure laboratory equipment and reagents | Purchase equipment that will improve the quality of research. | [13 empty] | 1. State of the art equipment purchased to improve quality of research |  | 20000 | 0 | 0 | Centre Leader, Leader, Project Manager, Procurement Officer, M&E Officer
Sub-Action 2c: Complete architectural planning for the WAGMC Building Complex and begin construction
Activity 1: Approve WAGMC Building drawings | Members of WAGMC Management review building drawings, provide feedback and approval. | [13 empty] | 1. Approved drawings |  | 0 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, ESS Officer, Physical Development & Municipal Services Directorate (PDMSD), UGCS
Activity 2: Submit all necessary documents for internal university approvals of the WAGMC Building Complex | Before construction begins all required documentation for permits will be submitted to the appropriate authorities for approval. | [13 empty] | 1. All Permits received |  | 10000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, ESS Officer, PDMSD
Activity 3: Begin procurement process including competitive tender for awarding contracts for the WAGMC Building Complex | Request for the services of contractors, engineers and other experts will be sent to the Logistics Directorate at the University of Ghana (UG) for procurement processes to be initiated. | [13 empty] | 1. All relevant contracts awarded |  | 20000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, ESS Officer, Procurement Officer, PDMSD
Activity 4: Begin first Phase of construction of the WAGMC building | Construction for ground floor begins | [13 empty] | 1. Work begins on site |  | 300000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, ESS Officer, Procurement Officer, PDMSD
Sub-Action 2d: Complete architectural planning for Vivarium and complete Construction
Activity 1: Engage consultants to design Vivarium | Consultants will be engaged to advise on design and functionality of the Vivarium | [13 empty] | 1. Consultants provide design for Vivarium | The Centre needs laboratory space sooner than the WAGMC building complex will be completed. | 10000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, ESS Officer, Procurement Officer, PDMSD
Activity 2: Award contract, begin and complete construction of Vivarium | Contracts will be awarded to experts to construct the Vivarium. | [13 empty] | 1. Completed Vivarium |  | 50000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, ESS Officer, Procurement Officer, PDMSD
Sub-Action 2e: Set up Telehealth platform and acquire appropriate software
Activity 1: Purchase and install software and hardware for telehealth platform | Procurement process will be initiated to begin purchasing of the components of the telehealth system. | [13 empty] | 1. Functional Telehealth educational platform |  | 40000 | 0 |  | Centre Leader, Project Manager, IT Officer, Procurement Officer, UGCS
Sub-Action 2f: Engagement of international faculty for teaching courses and workshops and co-supervision of students
Activity 1: Continue to engage international faculty in program development and teaching | WAGMC has had several meetings with international faculty from various university's including faculty from University of Cape Town and Witwatersrand University both in South Africa as well as faculty from Imperial College, UK. All of these faculty members have shown great interest and committed their time and expertise to help the Centre develop programs which will be offered in the next academic year. | Faculty from the various universities stated will participate in teaching students either through physical sessions on via online classes | [12 empty] | 1. Faculty and students exposed to current content, 2. Opportunity for research collaboration, 2. Exposure to international laboratory practices |  | 30000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, Education and Training Officer
Activity 2: Employ a part-time genetic counsellor to teach and take students through practicum | A genetic counsellor will be employed to teach in the newly developed MSc in Genetic Counselling Program the Centre has developed | [13 empty] | 1. Part-time genetic counsellor employed at the Centre | There is no faculty with training and accreditation in genetic counselling at the University of Ghana. The Centre will employ an accredited Genetic counsellor who will contribute to teaching and most importantly take students through the practical aspects of of genetic counselling. | 80000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, Education and Training Officer
Sub-Action 2g: Faculty Exchange programs with regional and national academic partners
Activity 1: Arrange for faculty members to visit academic partner institutions | Faculty members will visit academic partners for periods of about 1 to 2 weeks to observe and learn from other institutions and explore opportunities for research | Academic partners will host visiting faculty for periods of about 1 to 2 weeks. | [12 empty] | 1. Expose student and faculty to international standards of teaching and practise, 2. Opportunities for research and publication collaboration |  | 30000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Education and Training Officer
Action 3: Enhancing postgraduate training to achieve excellence with increasing quantity of students and a focus on gender and regionalization \DLI Action 3: Quantity of Students
Sub-Action 1a: Develop curricular for new postgraduate programs in medical genetics
Activity 1: Organize retreats to develop, evaluate and review educational programs | Plan an out of campus retreat for faculty to create a conducive environment for planning components of the programs | Faculty from partner institutions may be invited to participate in the retreat. | [12 empty] | 1. Curricula for the programs completed |  | 10000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer
Activity 2: Obtain University wide approval for the newly developed programs | The curricular of the newly developed programs will be submitted to various academic committees in the University for review and feedback and approval. | [13 empty] | 1. Approval from University Academic Committees received. |  | 0 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, UG Academic Committees
Activity 3: Submit newly approved programs to National Council of Tertiary Education (NCTE) for approval and apply for accreditation from National Accreditation Board (NAB) | The programs will be submitted to NCTE and NAB for approval and accreditation. | [13 empty] | 1. Approval from NCTE and accreditation by NAB |  | 10000 | 50000 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, M&E Officer, Education and Training Officer, UG Registrar
Sub-Action 2a: Enrol students into postgraduate programs
Activity 1: Enrol students into MSc/MPhil programs | Enrol students into various Programs at the University of Ghana | Scholarships for students from industry partners | [12 empty] | 1. Students enrolled into programs |  | 300000 | 150000 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Sectoral Liaison Officer, Education and Training Officer, UG Graduate School
Activity 2: Enrol students into PhD programs
Activity 2: Enrol students into Short Courses
Sub-Action 2b: Develop new curricula for short courses (topics include: precision medicine, pre-natal diagnosis, targeted therapy, genetic counselling)
Activity 1: Develop new short courses in Behavioural Genetics | New short courses will be developed and offered to students | Scholarships for students from industry partners | [12 empty] | 1. New Courses developed |  | 10000 | 10000 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Sectoral Liaison Officer, Education and Training Officer
Activity 2: Develop short courses in Medical Molecular Genetics | [14 empty] | 1. New Courses developed |  | 10000 | 10000 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Sectoral Liaison Officer, Education and Training Officer
Sub-Action 3c: Promoting innovative and translational research with increasing research publications
Activity 1: Build a research support unit (RSU) to provide data management, regulatory and compliance support to faculty and students to accelerate research and research training outputs, with competitive hiring of a bioethicist/data scientists and clinical research associates. | Advertise and employ bioethicist and clinical research associates, set up office for staff of RSU | [13 empty] | 1. Bioethicist/Data Scientists and clinical research associates employed within the RSU |  | 30000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, Communications Officer, M&E Officer
Activity 2: Recruit one full time staff scientist to support student training and development of new assays, grant applications and scientific writing. | A position for a fulltime staff scientist will be advertised after which applicants will be interviewed. | [13 empty] | 1. Fulltime staff scientist employed, 2. Efficient organisation and execution of student research projects, 3. Efficient coordination of preparation and submission of research publications and grant proposals |  | 30000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, Communications Officer, M&E Officer
Activity 3: Support Centre projects in laboratories that provide students high quality experience in research and mentoring | Students will be supported to conduct research in laboratories of partner institutions. | Support Centre with personnel and resources to expose students to current research practices/standards and well as provide mentorship to students | [12 empty] | 1. Experiential research for WAGMC students and increased faculty and student collaborative research |  | 20000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer
Activity 2: Determine the birth frequency, and the molecular bases of sickle-beta thalassemia(sickle-beta zero, and sickle beta-plus) in Ghana. | The Centre will work in partnership with the Sickle Cell Foundation of Ghana to collect samples for this activity. | Sickle Cell Foundation of Ghana runs national new born screening in Ghana. The foundation will collect and provide samples for the Centre to analyse. | [12 empty] | 1. Sites identified to commence data collection, 2. Study coordinators assigned to oversee and monitor the study, 3. Clinicians assigned to various sites to begin data collection |  | 25000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer, Sectoral Partners
Activity 3: Initiate joint genomics research projects with regional and national partners | Centre will initiate partnership activities to create opportunities to conduct collaborative research in genomics | Partner Institutions will avail researchers and resources for research activities. | [12 empty] | 1. Collaborative research projects between Centre and partner institutions, 2. Students co-supervised by regional faculty, 3. Regionally co-authored publications |  | 40000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer, Sectoral Partners
Activity 4: Investigate the molecular bases of rare genetic disorders in Ghana | Data collection and analysis | Rare Disease Ghana will work with the Centre to collect data for analysis | [12 empty] | 1.Data collection and analysis |  | 30000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer, Sectoral Partners
Activity 5. Sponsor short training visits for faculty and students | The Centre will make arrangements for short training visits for faculty and students | Sectoral partners will take on faculty and students for short training visits | [12 empty] | 1. Faculty and students complete training visits |  | 15000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer, Sectoral Partners
Action 4: Affirming relevance of education and research through externally generated revenue, internships, and entrepreneurship / DLI Action 5: Relevance of Education and Research Education /Research
Activity 1: Support faculty to work together with regional and international partners to sustain collaborative extramural funding to support genomics research | The Centre will support faculty to participate in retreats, workshops and seminars to increase opportunities for collaborative research. | [13 empty] | Advancement of research by faculty, increase in faculty derived funding for Centre’s research projects, increased faculty collaboration with regional and international partners |  | 20000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer, Sectoral Partners
Activity 2: Support faculty to submit at least 3 investigator-initiated grant applications and to publish peer-reviewed articles | Faculty will be provided with administrative support to write and submit grants. | Partners will be invited to contribute to grant applications. | [12 empty] | 1. Number of research projects available to students, 2. Funding opportunities for students who work with faculty members with grants, 3. Co-author opportunities for faculty |  | 10000 | 1000000 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer
Activity 3: Support faculty to publish peer-reviewed articles | The Centre will provide administrative support to faculty to publish articles and also pay publication related fees. | [13 empty] | 1. Increased number of faculty publications |  | 10000 | 200000 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer
Activity 4: Support PhD and Masters students to apply for small student grants from international agencies to support their research, attendance & presentations at scientific meetings | PhD and Masters students will be guided by faculty to write small grants. | Faculty from partner institutions may provided guidance to students. | [12 empty] | 1. Students improve their proposal writing ability, 2. Increased number of approved grants for students |  | 10000 | 20000 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer
Activity 5: Set up a DNA diagnosis confirmation unit for sickle cell disease | Acquire space for DNA Lab, remodel and furnish, and purchase research equipment | Sickle Cell Foundation of Ghana runs national new born screening in Ghana. The foundation will collect and provide samples for the Centre to analyse. | [12 empty] | 1. Increased number of patients tested for Sickle cell status, 2. Increased number of professionals trained to provide service to patients after diagnosis |  | 20000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer, Sectoral Partners
Action 5: Embarking on activities in collaboration with sectoral and industry partners to increase awareness of genetic diseases and provide access to genetic health across the West African Region \ DLI Action: 2 Development Impact
Activity 1: Organise public lectures in genetics in various locations both nationally and regionally | The Centre will organize public lectures beginning mid-year. These lectures will be held quarterly or bi-annually. | Partners will be invited to participate | [12 empty] | 1. Increase in awareness of genetic disorders among the population, 2. Increase in policies that ensure improvement in delivery of health care services for persons living with genetic disorders and their families. |  | 25000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Communications Officer
Activity 2: Plan and execute community and public engagement activities to promote the WAGMC project | The Centre will organize medical outreach events to provide free medical services to the general public with a focus on genetic conditions. Community engagement activities will be organized to educate citizens about genetic disorders and create awareness. | Partners will support activities by providing medical personnel and medical supplies for outreaches and community engagement activities | [12 empty] | 1. Improved access to genetic health services 2. Increases awareness of genetic disorders and its impact on individuals and their families, 3. Citizens able to make informed life decisions about their health and general wellbeing. |  | 50000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Communications Officer
Activity 3: Collaborate with Ghana Psychology Council (GPC) to regulate genetic counselling training programmes, and arrange and oversee internships for genetic counselling students | The Ghana Psychology Council (GPC) is the only body legally mandated to regulate the training and practice of psychologists and councellors in Ghana. The Council will therefore be responsble for developing and overseeing a new one-year internship programme for the MSc Genetic Counselling graduates WAGMC will produce, as well as organizing a licensure examinations for the Genetic Counsellors. The Centre will collaborate with the Council to develop this new national internship programme in Ghana by facilitating access to clinical training sites, and sharing with the Council a roster of accredited Genetic Councillors to contribute to the licensure examinations. | Regulation and placement of students in internship programmes. | [12 empty] | 1. Accredited programmes 2. Established internship programmes |  | 5000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Sectoral Liaison Officer, Education and Training Officer, M&E Officer, GPC
Activity 4: Collaborate with the Sickle Cell Foundation of Ghana to upgrade the national newborn screening for sickle cell disease in Ghana. | The Sickle Cell Foundation of Ghana (SCFG) runs a national New-born Screening for Sickle Cell Disease (SCD) programme in Ghana. Currently, the Foundation screens the blood of newborns using a single assay, iso-electric focusing (IEF) of hemoglobin. The Centre will start a new collaborative programme with the Foundation to povide a confirmatory hemoglobin electrophoresis test using its automated capillary elecrophoresis system for samples that are difficult to diagnose with IEF alone. In addition, the Centre and SCFG will collaborate to develop a new DNA-based assay to confirm challenging cases. | Personnel from Sickle Cell Foundation will work with the Centre to conduct genetic screening | [12 empty] | 1. Increase in availability of genetic testing services |  | 10000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Research Coordinator, M&E Officer, Sickle Cell Foundation of Ghana
Action 6: Promoting timeliness and quality of fiduciary management\ DLI Action: 6 Timeliness and Quality of FM
Activity 1: Timely financial reporting for the (WAGMC) ACE Account including timely submissions of Interim Financial Reports and audits reports | Administrative team will ensure that all reports are put together in a timely manner and submitted according to reporting timelines. | [13 empty] | 1. All financial reports repared and submitted. |  | 22000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, Finance Officer, Procurement Officer
Activity 2: Engage Internal and External auditors to conduct audits of the Centre and submit external audit reports to the UG Internal Audit Committee for review. | Management of the Centre will work with UG Internal Audit unit to audit the Centre's compliance to internal controls. | [13 empty] | 1. Internal and external audits conducted and reports duely submitted |  | 22000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, Finance Officer, Procurement Officer
Activity 3:Publish the approved budget, financial reports, annual work plan and the financial and procurement manuals of the Centre on the centre’s website to demonstrate transparency of expenses | All documents for timely and quality fiduciary management will be uploaded and updated regularly on the WAGMC Website | [13 empty] | 1. Budget, annual work plan and the financial and procurement manuals and reports accessible on the WAGMC Website |  | 22000 | 0 |  | Centre Leader, Deputy Centre Leader, Project Manager, Finance Officer, Procurement Officer, Communications Officer
Activity 4: Develop procurement plan for approval and ensure quality of procurement by conducting procurement audits as required. | Centre activities for the year will be reviewed to develop procurement plan for the current year. Procurement audit will also be done to ensure improvement of procurement activities. | [13 empty] | 1. Procurement audits conducted and reports submitted to the World Bank/AAU |  | 22000 | 0 | 0 | Centre Leader, Deputy Centre Leader, Project Manager, Finance Officer, Procurement Officer
Action 7: Undertake open, merit-based competitive selection of the head of the university and/or the department heads related to the ACE. t\ DLI Action: 7 Institutional Impact
Activity 1: Competitive selection of new Vice Chancellor of the University of Ghana | The term of the current Vice-Chancellor (VC) of the University of Ghana will expire on 31st July 2021. The Council of the University has formed a Search Panel to interview candidates for consideration for appoitment as the next VC using an open, merit-based competitive approach. The Centre will submit a memo to the Search Panel to advocate for the selection of a candidate who has clearly defined plans to address institutional challenges that are currently hindering research, and research manageent in the University. | [13 empty] | 1. Competive and strategic appointments of University and Department Heads |  | 0 | 250000 | 0 | HR Department of the University of Ghana, Registrar and Search Committee Members
Note on V6: Shinnied: If the addition of an activity or component requires further clarification, state it. Especially since COVID may alter center activities and focus